## Team
Initials | First | Last | Email | GitHub Username
NS | Naisargee | Shah | nshah53@stevens.edu | naisargee1
STJ | Sandesh | Jagadeesh | sandeshedu@gmail.com | sandesh1491
RT | Rakesh | Thippeswamy | rakesht4991@gmail.com | rakesht4991
|  |  | GitHub Repository: | CS555Group6

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Edited github file | N/A | RS | Done | 60 | 60 | 50 | 50 | 2015-03-01 | 2015-03-01
1 | US02 | Count number of male | p3 | STJ | Done | 60 | 60 | 50 | 50 | 2015-03-01 | 2015-03-01
3 | US03 | Checking if more male or female in family | p3 | STJ | Done | 60 | 60 | 55 | 60 | 2015-03-01 | 2015-03-01
4 | US04 | Check invalid email address | p4 | NS | Done | 60 | 60 | 65 | 60 | 2015-03-01 | 2015-03-01
5 | US05 | Check invalid phone number | p4 | NS | Done | 60 | 60 | 55 | 65 | 2015-03-01 | 2015-03-01
6 | US06 | Death before birth |  |  | next sprint
7 | US07 | Death before marriage |  |  | next sprint
8 | US08 | Death before marriage |  |  | next sprint
9 | US09 | Marriage before birth |  |  | next sprint
10 | US10 | Marriage before birth |  |  | next sprint

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Editing the github | Make sure you enter all the detailes that will help to prove the test stories. | N/A | 60 | 60
US02 | Number of males | Count the number of males in the family | p3 | 60 | 60
US03 | number of males or female | check whether the numbeer of male is greater or female is greater | p3 | 60 | 60
US04 | Check invalid email address | make sure the entered email address is valid (it must contain @ and .) | p4 | 60 | 60
US05 | Check invalid phone number | make sure the entered phone number is valid it should not be more or less than 10 digits. | p4 | 60 | 60

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Edited github file | Editing the files in order to test all the test condition in the user storis | N/A | Passed
AT03 | US02 | Count number of male | Input the file sandesh-family-1march.ged , if its not a valid file | Error message "Input file is invalid" | Failed
AT02 | US02 | Count number of male | Input the entire gedcom file to calculate the number of males | No error message | Passed
AT04 | US03 | Check wether number the males or females are grater in the family | Input the entire gedcom file to calculate the who is in grater strenght | No error message | Passed
AT05 | US03 | Check wether number the males or females are grater in the family | Input the file sandesh-family-1march.ged , if its not a valid file | Error message "Input file is invalid" | Failed
AT06 | US04 | Check invalid email address | Individual @I1@(sandesh Jagadeesh) has Email id Sandesh1491@gmail.com is valid | No error message | Passed
AT07 | US04 | Check invalid email address | Individual @I8@(champa sathish) has Email id champa.com is valid | Error message "Email id is invalid" | failed
AT08 | US05 | Check invalid phone number | Individual @I1@(sandesh Jagadeesh) has phone number 2012089396 is valid | No error message | passed
AT09 | US05 | Check invalid phone number | Individual @I8@(champa sathish) has phone number 656565665865 is invalid | Error message "The phone number is more than 10 digit " | failed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-03-01 | 25 |  | 0
2015-03-15 | 20 | 5 | 250 | 120 | 125
2015-03-29 | 15 | 5 | 400 | 90 | 100
2015-04-12 | 10 | 5 | 800 | 150 | 160
2015-04-26 | 5 | 5 | 900 | 80 | 75
| 0 | 5 | 1000 | 60 | 100

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Edited github file | N/A | RS | Done | 60 | 60 | 50 | 50 | 2015-03-01
US02 | Count number of male | P3 | STJ |  | 60 | 60 | 40 | 35 | 2015-03-01
P3:01 | find whether each individulal is male or not |  | STJ
P3:02 | calculate total number of males |  | STJ
US03 | Check male is greater or female is greater | p3 | STJ | DONE | 60 | 60 | 40 | 30 | 2015-03-01
P3:03 | Find number of females
P3:04 | compare number of males to number of females
US04 | Check invalid email address | p4 | NS | DONE | 60 | 60 | 45 | 40 | 2015-03-01
p4:01 | Read file and fetch Email address
p4:02 | Check wheather email address is valid or not
p4:03 | Print results
US05 | Check is contact number is valid or not | P4 | NS | DONE | 60 | 60 | 40 | 30 | 2015-03-01
p4:01 | Read file and fetch contact number
p4:02 | check with condition that contact number should be of 10 digits.
p4:03 | Print results

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed