## Team
Initials | First | Last | Email | GitHub Username
NS | Naisargee | Shah | nshah53@stevens.edu | naisargee1
STJ | Sandesh | Jagadeesh | sandeshedu@gmail.com | sandesh1491
RT | Rakesh | Thippeswamy | rakesht4991@gmail.com | rakesht4991
|  |  | GitHub Repository: | CS555Group6

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Edited github file | N/A | RT | Done | 60 | 60 | 50 | 50 | 2015-03-01 | 2015-03-01
1 | US02 | Count number of male | p3 | STJ | Done | 60 | 60 | 50 | 50 | 2015-03-01 | 2015-03-01
1 | US03 | Checking if more male or female in family | p3 | STJ | Done | 60 | 60 | 55 | 60 | 2015-03-01 | 2015-03-01
1 | US04 | Check invalid email address | p4 | NS | Done | 60 | 60 | 65 | 60 | 2015-03-01 | 2015-03-01
1 | US05 | Check invalid phone number | p4 | NS | Done | 60 | 60 | 55 | 65 | 2015-03-01 | 2015-03-01
2 | US06 | Death before birth | S1 | STJ | Done | 70 | 90 | 62 | 70 | 2015-03-15 | 2015-03-15
2 | US07 | Marriage before birth | s1 | STJ | Done | 70 | 90 | 62 | 70 | 2015-03-15 | 2015-03-15
2 | US08 | Place of birth of everyone in the family | r1 | STJ | Done | 70 | 90 | 62 | 65 | 2015-03-15 | 2015-03-15
2 | US09 | Birth before death | n1 | NS | Done | 70 | 90 | 61 | 80 | 2015-03-15 | 2015-03-15
2 | US10 | Death before marriage | n1 | NS | Done | 70 | 90 | 61 | 80 | 2015-03-15 | 2015-03-15
2 | US11 | Finding ages of all the family members | N1 | NS | Done | 70 | 90 | 61 | 70 | 2015-03-15 | 2015-03-15
2 | US12 | Given name of all the members | r1 | RT | Done | 70 | 90 | 25 | 60 | 2015-03-15 | 2015-03-15
2 | US13 | Finding number of members of the family | S1 | RT | Done | 70 | 90 | 25 | 60 | 2015-03-15 | 2015-03-15
3 | US14 | Invalid age | n1 | NS | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US15 | Divorce before birth | n1 | NS | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US16 | Divorce before marriage | n1 | NS | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US17 | Divorce after death | s1 | STJ | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US18 | Divorce after marriage | s1 | STJ | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US19 | Invalid date of birth | s1 | STJ | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US20 | Divorce dates | r1 | RT | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US21 | count families | r1 | RT | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
3 | US22 | number of dead people | r1 | RT | Done | 60 | 60 |  |  | 2015-03-29 | 2015-03-29
4 | US23 | Child should be born before death of mother | n1 | NS | SPRINT4
4 | US24 | Child should be born before 9 months after death of father | n1 | NS | S4
4 | US25 | Marriage should be at least 14 years after birth of both spouses | s1 | STJ | S4
4 | US26 | Mother should be less than 60 years older than her children | s1 | STJ | S4
4 | US27 | Father should be less than 80 years older than his children | r1 | RT | S4
4 | US28 | Siblings should be more than 8 months apart in birth dates | r1 | RT | S4
4 | US29 | born on leap year | N1 | NS | S4
4 | US30 | marriageon leap year | s1 | STJ | S4
4 | US31 | death on leap year | R1 | RT | S4

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Editing the github | Make sure you enter all the detailes that will help to prove the test stories. | N/A | 60 | 60
US02 | Number of males | Count the number of males in the family | p3 | 60 | 60
US03 | number of males or female | check whether the numbeer of male is greater or female is greater | p3 | 60 | 60
US04 | Check invalid email address | make sure the entered email address is valid (it must contain @ and .) | p4 | 60 | 60
US05 | Check invalid phone number | make sure the entered phone number is valid it should not be more or less than 10 digits. | p4 | 60 | 60
US06 | Death before birth | Checking wether any peerson death date is before birthdate | S1 | 70 | 90
US07 | Marriage before birth | Checking wetherany person marriage date is before birthdate | S1 | 70 | 90
US08 | Place of birth of everyone in the family | Printing everyones place of birth | S1 | 70 | 90
US09 | Birth before death | Checking anyone birthdate is before his deathdate | N1 | 70 | 90
US10 | Death before marriage | Checking anyone deathdate is before his marriagedate | N1 | 70 | 90
US11 | Finding ages of all the family members | Finding ages of all the family members at this present year | N1 | 70 | 90
US12 | Given name of all the family members | first part of our next sprint user story, to print all the given names. | R1 | 70 | 90
US13 | Finding number of members of the family | To keep update we need to find total number of members in the family | R1 | 70 | 90
US14 | Invalid age | To find individual who's age is more than 150 years | N1 | 60 | 90
US15 | Divorce before birth | checking who's divorce date is before birthdate | N1 | 60 | 90
US16 | Divorce before marriage | checking who's divorce date is before marriage date | N1 | 60 | 90
US17 | Divorce after death | checking who's divorce date is after death date | S1 | 60 | 90
US18 | Divorce after marriage | names of the persons who has divorced in the family | S1 | 60 | 90
US19 | Invalid date of birth | checking who's date of birth is grater than present day | S1 | 60 | 90
US20 | Divorce dates | print the divorce date of the family members | R1 | 60 | 90
US21 | count families | count number of families | R1 | 60 | 90
US22 | number of dead people | Finding number of dead persons in the family | R1 | 60 | 90

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Edited gedcom file | Editing the files in order to test all the test condition in the user storis | N/A | Passed
AT03 | US02 | Count number of male | Input the file sandesh-family-1march.ged , if its not a valid file | Error message "Input file is invalid" | Failed
AT02 | US02 | Count number of male | Input the entire gedcom file to calculate the number of males | No error message | Passed
AT04 | US03 | Check wether number the males or females are grater in the family | Input the entire gedcom file to calculate the who is in grater strenght | No error message | Passed
AT05 | US03 | Check wether number the males or females are grater in the family | Input the file sandesh-family-1march.ged , if its not a valid file | Error message "Input file is invalid" | Failed
AT06 | US04 | Check invalid email address | Individual @I1@(sandesh Jagadeesh) has Email id Sandesh1491@gmail.com is valid | No error message | Passed
AT07 | US04 | Check invalid email address | Individual @I8@(champa sathish) has Email id champa.com is valid | Error message "Email id is invalid" | passed
AT08 | US05 | Check invalid phone number | Individual @I1@(sandesh Jagadeesh) has phone number 2012089396 is valid | No error message | passed
AT09 | US05 | Check invalid phone number | Individual @I8@(champa sathish) has phone number 656565665865 is invalid | Error message "The phone number is more than 10 digit " | passed
AT10 | US06 | Death before birth | Individual @I13@ has the birth date (1932) and deathrate(1926) | Error message "Death can't happen before birth for Venkatapa Kolapur" | passed
AT11 | US07 | Marriage before birth | Individual @I13@ has the birth date (2000) and marriagedate(1975) | Error message " Marriage can't happen before birth for Sundar Lone " | passed
AT12 | US08 | Place of birth of everyone in the family | Individual @I1@ sandesh jagadeesh has birth place tumkur | message" birth place for Sandesh Jagadeesh is tumkur" | passed
AT13 | US09 | Birth before death | Individual @19@ Lakshmi venkatapa has deathdate(1965) has birth(1975) | Error message " Birth cannot happen before death for Lakshmi Venkatapa" | passed
AT14 | US10 | Death before marriage | Individual @18@ Dona lona has death (1920) and marrigedate(1930) | Error message "Death can't happen before marriage for Donna Lone" | passed
AT15 | US11 | Finding ages of all the family members | Individual @I1@ sandesh jagadeesh has age of 24 | Success message "age of Sandesh Jagadeesh is 24" | passed
AT16 | US12 | Given name of the family members | Individual @I3@ kusuma Jagadeesh has given name kusuma | Success message "kusuma" | passed
AT17 | US13 | Finding number of members of the family | N/A( part used in next sprint user stories) | Success message " Total number of Individual are : 21" ( as per P6) | Passed
AT18 | US14 | Invalid age | Individual @I11@ John harry has age of 170 | Error message " invalid data as death year is after 150 year of birth year which is practically not possible like John Harry 170" | Passed
AT19 | US14 | Invalid age | Individual @I19@ Lakshmi venkatapa has age of 20 | No error message | passed
AT20 | US15 | Divorce before birth | Individual @I18@Donna lone has birth year 1980 and divorce on 1940 | Error message "Divorce cannot happen before birth Donna Lone" | passed
AT21 | US15 | Divorce before birth | Individual @I25@ Sable lucas has birthyear 2020 and divorce on 2044 | No error message | Passed
AT22 | US16 | Divorce before marriage | Individual @I22@Jackson venkatapa has marriage date on 2020 and divorce on 2000 | Error message "Divorce cannot happen before marraige for Jackson Venkatapa" | passed
AT23 | US16 | Divorce before marriage | Individual @I25@ sable lucas has marruage on 2033 and divorce on 2044 | No error message | passed
AT24 | US17 | Divorce after death | Individual @I27@ Noah kiddi has death date on 2031 and divorce on 2044 | Error message "Divorce cannot happen after death Noah Kiddi" | passed
AT25 | US17 | Divorce after death | Individual @I17@ Dodapa venkatapa has death date on 2001 and divorce on 1995 | No error message | passed
AT26 | US18 | Divorce after marriage | Individual @I27@ Noah kiddi has marriage on 1930 and divorce on 1940 | No error message | passed
AT27 | US19 | Invalid date of birth | Individual @I23@ Abby jackson has birthdate 2018 but present date is 2015 | Error message " Person is not yet born Abby Jackson" | passed
AT28 | US19 | Invalid date of birth | Individual @I01@ Sandesh jagadeesh has birthdate 1991 but present date is 2015 | No error message | passed
AT29 | US20 | Divorce dates | Sachi Venkatapa has divorce date on 19 NOV 2056 | No error message | passed
AT30 | US21 | count families | count the number of familes | success message "Total number of families are :12 " | passed
AT31 | US22 | number of dead people | Number of individual who are dead in the family | Success message " number of dead people are : 6" | passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-28 | 30 |  | 0
2015-03-01 | 25 | 5 | 223 | 160 | 83.625
2015-03-15 | 17 | 8 | 310 | 280 | 18.6429
2015-03-28 | 8 | 9 | 348 | 300 | 7.6
|  |  | 900 | 80 | 414
|  |  | 1000 | 60 | 100

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Edited github file | N/A | RS | Done | 60 | 60 | 50 | 50 | 2015-03-01
US02 | Count number of male | P3 | STJ |  | 60 | 60 | 40 | 35 | 2015-03-01
P3:01 | find whether each individulal is male or not |  | STJ
P3:02 | calculate total number of males |  | STJ
US03 | Check male is greater or female is greater | p3 | STJ | DONE | 60 | 60 | 40 | 30 | 2015-03-01
P3:03 | Find number of females
P3:04 | compare number of males to number of females
US04 | Check invalid email address | p4 | NS | DONE | 60 | 60 | 45 | 40 | 2015-03-01
p4:01 | Read file and fetch Email address
p4:02 | Check wheather email address is valid or not
p4:03 | Print results
US05 | Check is contact number is valid or not | P4 | NS | DONE | 60 | 60 | 40 | 30 | 2015-03-01
p4:01 | Read file and fetch contact number
p4:02 | check with condition that contact number should be of 10 digits.
p4:03 | Print results

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | Death before birth | S1 | STJ | DONE | 70 | 90 | 61 | 60
s1:01 | Find indiviual birth date | S1
s1:02 | Find indiviual birth date | S1
s1:03 | Find Death before birth | S1
US07 | Marriage before birth | S1 | STJ | DONE | 70 | 90 | 61 | 60
s1:04 | find Birth date | S1
s1:05 | find marriage date | S1
s1:06 | Find marriage before birth | S1
US08 | Place of birth of everyone in the family | S1 | STJ | DONE | 70 | 90 | 61 | 60
S1:07 | Find the indiviual | s1
S1:08 | Print the birth place | s1
US09 | Birth before death | N1 | NS | DONE | 70 | 90 | 62 | 60
N1:01 | Find indiviual birth date | n1
N1:02 | Find indiviual Death date | n1
N1:03 | Find birth before death | n1
US10 | Death before marriage | N1 | NS | DONE | 70 | 90 | 62 | 60
N1:04 | find Birth date | N1
N1:05 | find marriage date | N1
N1:06 | Find marriage before birth | N1
US11 | Finding ages of all the family members | N1 | NS | DONE | 70 | 90 | 62 | 60
N1:07 | Find the date of birth | N1
N1:08 | find present year | N1
N1:09 | Find ages | n1
US12 | Given name of all the members | R1 | RS | DONE | 70 | 90 | 25 | 30
R1:01 | Find Individual | r1
R2:02 | Print given names | r1
US13 | Finding number of members of the family | R1 | RS | Done | 70 | 90 | 25 | 30
R1:01 | Fibd number of indiviual | r1
R2:02 | Count number of members | r1
REVIEW
we have done 3 java files which check all the user stories
The error messages and successful both taken in equal measure
Finally sprint is finished in time and made meeting what should be done in sprint 3

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US14 | Invalid age | n1 | NS | DONE | 60 | 90 | 24 | 45 | 2015-03-29
n1:01 | Find the birthdate
n1:02 | find the deathdate
n1:03 | find age
US15 | Divorce before birth | n1 | NS | DONE | 60 | 90 | 29 | 45 | 2015-03-29
n1:04 | find the birthdate
n1:05 | find the divorce date
n1:06 | check condition
US16 | Divorce before marriage | n1 | NS | DONE | 60 | 90 | 24 | 45 | 2015-03-29
n1:07 | Find marriage date
n1:08 | Find divorce date
n1:09 | Check condition
US17 | Divorce after death | s1 | STJ | DONE | 60 | 90 | 25 | 45 | 2015-03-29
S1:01 | Find death date
S1:02 | Find divorce date
S1:03 | Check the condition
US18 | Divorce after marriage | s1 | STJ | DONE | 60 | 90 | 25 | 45 | 2015-03-29
S1:04 | Find the marriage date
S1:05 | find the divorce date
S1:06 | print the names of divorced people
US19 | Invalid date of birth | s1 | STJ | DONE | 60 | 90 | 14 | 45 | 2015-03-29
S1:07 | Find date of birth
S1:08 | find present year
S1:09 | check DOB more than present day
US20 | Divorce dates | r1 | RT | DONE | 60 | 90 | 16 | 40 | 2015-03-29
R1:01 | Find the divorce dates
R1:02 | print the dates
US21 | count families | r1 | RT | DONE | 60 | 90 | 8 | 30 | 2015-03-29
R1:03 | Count the number of familes
R1:04 | print the total number of families
US22 | number of dead people | r1 | RT | DONE | 60 | 90 | 15 | 35 | 2015-03-29
R1:05 | Find the death date
R1:06 | count the number of people dead
R1:07 | print the count
REVIEW
In this sprint we have done 9 users stories each team member has done 3 stories each.
we have taken approximatly 90 min as an average time to finish off.
In the above table loc is only loc of that particular method not complete methods loc.
we have left with 8 more user stories in the next two sprints.
In this sprint we have mainly concentrated on divorce relationship.

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US23 | Child should be born before death of mother | n1 | NS | SPRINT 4
US24 | Child should be born before 9 months after death of father | n1 | NS | SPRINT 5
US25 | Marriage should be at least 14 years after birth of both spouses | s1 | STJ | SPRINT 6
US26 | Mother should be less than 60 years older than her children | s1 | STJ | SPRINT 7
US27 | Father should be less than 80 years older than his children | r1 | RT | SPRINT 8
US28 | Siblings should be more than 8 months apart in birth dates | r1 | RT | SPRINT 9
US29 | born on leap year | N1 | NS | SPRINT 10
US30 | marriageon leap year | s1 | STJ | SPRINT 11
US31 | death on leap year | R1 | RT | SPRINT 12

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed