## Team
Initials | First | Last | Email | GitHub Username
NS | Naisargee | Shah | nshah53@stevens.edu | naisargee1
STJ | Sandesh | Jagadeesh | sandeshedu@gmail.com | sandesh1491
RT | Rakesh | Thippeswamy | rakesht4991@gmail.com | rakesht4991
|  |  | GitHub Repository: | CS555Group6

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Edited github file | N/A | RT | Done | 60 | 60 | 50 | 50 | 2015-03-01 | 2015-03-01
1 | US02 | Count number of male | p3 | STJ | Done | 60 | 60 | 50 | 50 | 2015-03-01 | 2015-03-01
3 | US03 | Checking if more male or female in family | p3 | STJ | Done | 60 | 60 | 55 | 60 | 2015-03-01 | 2015-03-01
4 | US04 | Check invalid email address | p4 | NS | Done | 60 | 60 | 65 | 60 | 2015-03-01 | 2015-03-01
5 | US05 | Check invalid phone number | p4 | NS | Done | 60 | 60 | 55 | 65 | 2015-03-01 | 2015-03-01
6 | US06 | Death before birth | S1 | STJ | Done | 70 | 90 | 62 | 70 | 2015-03-15 | 2015-03-15
7 | US07 | Marriage before birth | s1 | STJ | Done | 70 | 90 | 62 | 70 | 2015-03-15 | 2015-03-15
8 | US08 | Place of birth of everyone in the family | r1 | STJ | Done | 70 | 90 | 62 | 65 | 2015-03-15 | 2015-03-15
9 | US09 | Birth before death | n1 | NS | Done | 70 | 90 | 61 | 80 | 2015-03-15 | 2015-03-15
10 | US10 | Death before marriage | n1 | NS | Done | 70 | 90 | 61 | 80 | 2015-03-15 | 2015-03-15
11 | US11 | Finding ages of all the family members | N1 | NS | Done | 70 | 90 | 61 | 70 | 2015-03-15 | 2015-03-15
12 | US12 | Given name of all the members | r1 | RT | Done | 70 | 90 | 25 | 60 | 2015-03-15 | 2015-03-15
13 | US13 | Finding number of members of the family | S1 | RT | Done | 70 | 90 | 25 | 60 | 2015-03-15 | 2015-03-15

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Editing the github | Make sure you enter all the detailes that will help to prove the test stories. | N/A | 60 | 60
US02 | Number of males | Count the number of males in the family | p3 | 60 | 60
US03 | number of males or female | check whether the numbeer of male is greater or female is greater | p3 | 60 | 60
US04 | Check invalid email address | make sure the entered email address is valid (it must contain @ and .) | p4 | 60 | 60
US05 | Check invalid phone number | make sure the entered phone number is valid it should not be more or less than 10 digits. | p4 | 60 | 60
US06 | Death before birth | Checking wether any peerson death date is before birthdate | S1 | 70 | 90
US07 | Marriage before birth | Checking wetherany person marriage date is before birthdate | S1 | 70 | 90
US08 | Place of birth of everyone in the family | Printing everyones place of birth | S1 | 70 | 90
US09 | Birth before death | Checking anyone birthdate is before his deathdate | N1 | 70 | 90
US10 | Death before marriage | Checking anyone deathdate is before his marriagedate | N1 | 70 | 90
US11 | Finding ages of all the family members | Finding ages of all the family members at this present year | N1 | 70 | 90
US12 | Given name of all the family members | first part of our next sprint user story, to print all the given names. | R1 | 70 | 90
US13 | Finding number of members of the family | To keep update we need to find total number of members in the family | R1 | 70 | 90

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Edited gedcom file | Editing the files in order to test all the test condition in the user storis | N/A | Passed
AT03 | US02 | Count number of male | Input the file sandesh-family-1march.ged , if its not a valid file | Error message "Input file is invalid" | Failed
AT02 | US02 | Count number of male | Input the entire gedcom file to calculate the number of males | No error message | Passed
AT04 | US03 | Check wether number the males or females are grater in the family | Input the entire gedcom file to calculate the who is in grater strenght | No error message | Passed
AT05 | US03 | Check wether number the males or females are grater in the family | Input the file sandesh-family-1march.ged , if its not a valid file | Error message "Input file is invalid" | Failed
AT06 | US04 | Check invalid email address | Individual @I1@(sandesh Jagadeesh) has Email id Sandesh1491@gmail.com is valid | No error message | Passed
AT07 | US04 | Check invalid email address | Individual @I8@(champa sathish) has Email id champa.com is valid | Error message "Email id is invalid" | failed
AT08 | US05 | Check invalid phone number | Individual @I1@(sandesh Jagadeesh) has phone number 2012089396 is valid | No error message | passed
AT09 | US05 | Check invalid phone number | Individual @I8@(champa sathish) has phone number 656565665865 is invalid | Error message "The phone number is more than 10 digit " | failed
AT10 | US06 | Death before birth | Individual @I13@ has the birth date (1932) and deathrate(1926) | Error message "Death can't happen before birth for Venkatapa Kolapur" | Failure
AT11 | US07 | Marriage before birth | Individual @I13@ has the birth date (2000) and marriagedate(1975) | Error message " Marriage can't happen before birth for Sundar Lone " | Failure
AT12 | US08 | Place of birth of everyone in the family | Individual @I1@ sandesh jagadeesh has birth place tumkur | message" birth place for Sandesh Jagadeesh is tumkur" | Succesful
AT13 | US09 | Birth before death | Individual @19@ Lakshmi venkatapa has deathdate(1965) has birth(1975) | Error message " Birth cannot happen before death for Lakshmi Venkatapa" | Failure
AT14 | US10 | Death before marriage | Individual @18@ Dona lona has death (1920) and marrigedate(1930) | Error message "Death can't happen before marriage for Donna Lone" | Failure
AT15 | US11 | Finding ages of all the family members | Individual @I1@ sandesh jagadeesh has age of 24 | Success message "age of Sandesh Jagadeesh is 24" | Succesfull
AT16 | US12 | Given name of the family members | Individual @I3@ kusuma Jagadeesh has given name kusuma | Success message "kusuma" | Successful
AT17 | US13 | Finding number of members of the family | N/A( part used in next sprint user stories) | Success message " Total number of Individual are : 21" ( as per P6) | Successful

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-03-01 | 25 |  | 0
2015-03-15 | 17 |  | 250 | 120 | 125
2015-03-29 |  |  | 400 | 90 | 100
2015-04-12 |  |  | 800 | 150 | 160
2015-04-26 |  |  | 900 | 80 | 75
|  |  | 1000 | 60 | 100

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Edited github file | N/A | RS | Done | 60 | 60 | 50 | 50 | 2015-03-01
US02 | Count number of male | P3 | STJ |  | 60 | 60 | 40 | 35 | 2015-03-01
P3:01 | find whether each individulal is male or not |  | STJ
P3:02 | calculate total number of males |  | STJ
US03 | Check male is greater or female is greater | p3 | STJ | DONE | 60 | 60 | 40 | 30 | 2015-03-01
P3:03 | Find number of females
P3:04 | compare number of males to number of females
US04 | Check invalid email address | p4 | NS | DONE | 60 | 60 | 45 | 40 | 2015-03-01
p4:01 | Read file and fetch Email address
p4:02 | Check wheather email address is valid or not
p4:03 | Print results
US05 | Check is contact number is valid or not | P4 | NS | DONE | 60 | 60 | 40 | 30 | 2015-03-01
p4:01 | Read file and fetch contact number
p4:02 | check with condition that contact number should be of 10 digits.
p4:03 | Print results

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | Death before birth | S1 | STJ | DONE | 70 | 90 | 61
s1:01 | Find indiviual birth date | S1
s1:02 | Find indiviual birth date | S1
s1:03 | Find Death before birth | S1
US07 | Marriage before birth | S1 | STJ | DONE | 70 | 90 | 61
s1:04 | find Birth date | S1
s1:05 | find marriage date | S1
s1:06 | Find marriage before birth | S1
US08 | Place of birth of everyone in the family | S1 | STJ | DONE | 70 | 90 | 61
S1:07 | Find the indiviual | s1
S1:08 | Print the birth place | s1
US09 | Birth before death | N1 | NS | DONE | 70 | 90 | 62
N1:01 | Find indiviual birth date | n1
N1:02 | Find indiviual Death date | n1
N1:03 | Find birth before death | n1
US10 | Death before marriage | N1 | NS | DONE | 70 | 90 | 62
N1:04 | find Birth date | N1
N1:05 | find marriage date | N1
N1:06 | Find marriage before birth | N1
US11 | Finding ages of all the family members | N1 | NS | DONE | 70 | 90 | 62
N1:07 | Find the date of birth | N1
N1:08 | find present year | N1
N1:09 | Find ages | n1
US12 | Given name of all the members | R1 | RS | DONE | 70 | 90 | 25
R1:01 | Find Individual | r1
R2:02 | Print given names | r1
US13 | Finding number of members of the family | R1 | RS | Done | 70 | 90 | 25
R1:01 | Fibd number of indiviual | r1
R2:02 | Count number of members | r1
REVIEW
we have done 3 java files which check all the user stories
The error messages and successful both taken in equal measure
Finally sprint is finished in time and made meeting what should be done in sprint 3

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
Divorce should be before death of both spouses
Death should be less than 150 years after birth
Current date should be less than 150 years after birth for all living people
Child should be born before death of mother
Child should be born before 9 months after death of father
Marriage should be at least 14 years after birth of both spouses
Mother should be less than 60 years older than her children
Father should be less than 80 years older than his children

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed